A&J LUXURY MOBILE APP

Quotation, Readiness Checklist and 3-Month Development Plan

Android app for buying and consigning luxury items in the Philippines

Date: 24 October 2026  ·  Currency: Philippine peso (₱)  ·  Prices checked: 23–24 October 2026

# Contents

- 1. Summary of costs

- 2. Assumptions used for the estimates

- 3. Quotation of possible expenses (development period and first year)

- 4. Publish and run readiness checklist

- 5. Three-month Gantt chart and task table

- 6. Uncertain or unavailable information

- 7. Sources

# 1. Summary of costs

All amounts are estimates in Philippine pesos. Details, sources and the required or optional status of each item are in section 3.

| Development period (12 weeks): required items, without team pay | ₱250,420 |
| --- | --- |
| Development team pay (12 weeks) | ₱577,500 |
| Contingency (15% of the two lines above) | ₱124,188 |
| Grand total, 3-month development (required + team + contingency) | ₱952,108 |
| Grand total, 3-month development, including all optional items | ₱992,441 |
| If the app is built by an existing unpaid team (required items + 15%) | ₱287,983 |
| First-year running costs after launch (required + 10% contingency) | ₱429,022 |
| First-year running costs, including all optional items | ₱768,538 |

Payment provider fees are not in these totals. They depend on sales and are often passed to the buyer. Example for a ₱100,000 item: card ₱3,515, GCash ₱2,500, QR Ph ₱1,500 (rates from PayMongo [3]).

# 2. Assumptions used for the estimates

Price markers used in all tables: V = verified from the cited source; E = our estimate; U = could not be verified; Free = no cost. A number in brackets, such as [4], points to section 7.

## Team and schedule

- Team of five: Android developer, backend/web developer, UI/UX designer (2 months), QA tester (1.5 months) and a part-time project lead.

- Team members work remotely on their own laptops. No office rent, laptops or internet are included.

- Pay is shown as a monthly rate. If people are hired as employees, add 13th-month pay and employer SSS, PhilHealth and Pag-IBIG shares (not included).

- Development runs 12 weeks. Monthly subscriptions are counted for 3 months unless the table says otherwise.

## Technology

- Android app (Kotlin or Flutter) for phones, targeting Android 16 (API level 36), which Google Play requires for new apps from 31 August 2026 [19].

- Supabase Pro for database, login and photo storage; Firebase for push alerts, crash reports and analytics; admin dashboard as a small website.

- Chatbot uses fixed answers approved by A&J (as in the prototype). An AI model is an optional upgrade.

- In-app payment through PayMongo is optional. The base plan keeps the current flow: inquiry first, then A&J sends payment details.

## Users and usage (first year)

- Up to 5,000 registered users and about 1,000 monthly active users.

- Up to 2,000 items with about 10 photos each (about 6 GB). This fits the Supabase Pro plan limits.

- If the AI chatbot is used: 3,000 chats a month, 5 messages each, about 2,000 input and 300 output tokens (word pieces) per message.

## Money and taxes

- Exchange rate: US$1 = ₱61. The latest rate we could verify was ₱60.99 on 4 August 2026 [6]. No October 2026 rate was found, so recheck before paying.

- Foreign online services (Supabase, Figma, GitHub, Sentry, Freshdesk, AI API) may add 12% VAT on digital services under RA 12023 [22]. Prices shown exclude this VAT. The contingency covers it.

- A&J's business registration, BIR registration and permits already exist and are not costed here.

- A&J already owns a website domain; buying a new .com.ph domain is therefore optional.

- No pictures from the A&J Luxury website are used in this document or budgeted for use. Photos come from a new photo shoot or free-licence libraries.

# 3. Quotation of possible expenses

Table 3.1 lists every expense we expect while preparing, building and publishing the app. “Est. cost” is the price per unit (per month, per year or once). “Cost in 3-month build” is what that item costs during the 12-week development period.

## 3.1 Development period (12 weeks)

| Category | Item | Description | Est. cost (PHP) | Cost type | Required / optional | Cost in 3-month build (PHP) | Basis |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Google Play Console developer account | Developer registration fee | US$25, paid once. Covers all future apps. Prepaid cards are not accepted. | ₱1,525 | One-time | Required | ₱1,525 | V [1] |
| Google Play Console developer account | D-U-N-S number (organisation account) | Google asks organisations for a D-U-N-S number. Dun & Bradstreet issues it free, but it can take days to weeks. | ₱0 | One-time | Required | ₱0 | E |
| Google Play Console developer account | Google Play commission on sales | A&J sells physical goods, so Google Play Billing is not used and Google takes no commission. | ₱0 | Per sale | Required | Varies | V [2] |
| Subtotal – Google Play Console developer account: required ₱1,525 · optional ₱0 |  |  |  |  |  | ₱1,525 |  |
| Development tools, software and licences | Android Studio, Kotlin/Flutter SDK, Git | Official tools are free. Team uses its own laptops (see assumptions). | ₱0 | One-time | Required | ₱0 | Free |
| Subtotal – Development tools, software and licences: required ₱3,660 · optional ₱2,928 |  |  |  |  |  | ₱6,588 |  |
| Backend hosting, database and cloud storage | Supabase Pro (live project) | US$25/month: database, login, file storage (100 GB), 250 GB transfer. Includes US$10 credit for one Micro server. | ₱1,525 | Monthly | Required | ₱4,575 | V [4] |
| Backend hosting, database and cloud storage | Second project for staging/testing | Extra Micro server, about US$10/month. Keeps test data away from real data. | ₱610 | Monthly | Optional | ₱1,830 | V [4] |
| Backend hosting, database and cloud storage | Firebase: push alerts, crash reports, analytics | Cloud Messaging, Crashlytics and Analytics are no-cost Firebase products. | ₱0 | Monthly | Required | ₱0 | V [5] |
| Backend hosting, database and cloud storage | Hosting for admin website and privacy policy page | Free tier of a static host (for example Netlify, Vercel or GitHub Pages). | ₱0 | Monthly | Required | ₱0 | E |
| Subtotal – Backend hosting, database and cloud storage: required ₱4,575 · optional ₱1,830 |  |  |  |  |  | ₱6,405 |  |
| Domain, SSL and email | Domain name (.com.ph) | About US$45/year at a third-party registrar. ₱0 if A&J uses its current website domain. | ₱2,745 | Yearly | Optional | ₱2,745 | V [7] |
| Domain, SSL and email | SSL certificates | Free and automatic with Supabase and the static host. | ₱0 | Yearly | Required | ₱0 | E |
| Domain, SSL and email | Business email, 2 users (Google Workspace Starter) | ₱280 per user per month from a Philippine reseller. For support@ and privacy@ addresses. | ₱560 | Monthly | Required | ₱1,680 | V [8] |
| Subtotal – Domain, SSL and email: required ₱1,680 · optional ₱2,745 |  |  |  |  |  | ₱4,425 |  |
| Payment provider fees | PayMongo account | No set-up fee was found. Business documents are needed to activate. Only if in-app payment is used. | ₱0 | One-time | Optional | ₱0 | E |
| Payment provider fees | Transaction fees (in-app payment only) | Card 3.5% + ₱15; GCash 2.5%; QR Ph 1.5% per payment. Test mode is free during development. | 3.5%+₱15 / 2.5% / 1.5% | Per sale | Optional | Varies | V [3] |
| Subtotal – Payment provider fees: required ₱0 · optional ₱0 |  |  |  |  |  | ₱0 |  |
| Chatbot service / AI API usage | FAQ chatbot with fixed, approved answers | Same approach as the prototype. Built by the team; no API cost. | ₱0 | Monthly | Required | ₱0 | Free |
| Chatbot service / AI API usage | AI model API, testing during development | About US$10/month of test usage if the AI upgrade is chosen. | ₱610 | Monthly | Optional | ₱1,830 | E [9] |
| Subtotal – Chatbot service / AI API usage: required ₱0 · optional ₱1,830 |  |  |  |  |  | ₱1,830 |  |

# 4. Publish and run readiness checklist

Tick each box when done. Owners are suggestions and can be changed.

## Stage 1 – Before development

| Done | What to prepare | Details | Owner |
| --- | --- | --- | --- |
| ☐ | Open a Google Play Console account in A&J's company name (organisation account) | Needs a D-U-N-S number, identity check and 2-step verification. Start in week 1: checks can take days or weeks. Personal accounts made after November 2023 must also run a 12-tester, 14-day closed test before production [21]. | Project lead |
| ☐ | Pay the US$25 registration fee with a credit or debit card | Prepaid cards are not accepted [1]. | A&J |
| ☐ | Put every account in A&J's name with at least two admins | Play Console, Supabase, Firebase, PayMongo, domain and email. Use company emails, not personal ones. | Project lead |
| ☐ | Confirm policies with A&J | Shipping fees, card fee, returns, consignment terms, payout rules and showroom address differ between website pages. | Project lead + A&J |
| ☐ | Get written permission for photos and brand assets | Do not use any picture from the A&J website until permission is given in writing. | Project lead |
| ☐ | Name a privacy contact (Data Protection Officer) | Check whether NPC registration is required or a sworn declaration is enough [16]. | A&J |
| ☐ | List the personal data the app will collect and why | Collect only what is needed. Consignor government IDs are sensitive and need extra care and a retention period. | Backend dev + DPO |
| ☐ | Fix the technical baseline | Target Android 16 (API 36) [19]; separate staging and live projects; no passwords or keys in the code. | Developers |
| ☐ | Decide the payment approach | Inquiry-first (as now) or PayMongo in-app. Physical goods do not use Google Play Billing [2]. | A&J + project lead |
| ☐ | Engage a lawyer | Terms of Service, Privacy Notice, consignment and seller terms. Ask about the Data Privacy Act, Internet Transactions Act and Consumer Act. | Project lead |

## Stage 2 – Before testing

| Done | What to prepare | Details | Owner |
| --- | --- | --- | --- |
| ☐ | Create the upload key and turn on Play App Signing | Keep the key file and passwords in two safe places (password manager and offline backup). Losing it delays updates. | Android dev |
| ☐ | Build releases as an Android App Bundle (.aab) | Google Play requires the .aab format for new apps. | Android dev |
| ☐ | Lock down the database | Turn on row-level security on every table. Test that one user cannot see another user's data. Separate admin roles. | Backend dev |
| ☐ | Connect crash reports and analytics | Crashlytics and Analytics must work before testers start, so problems are captured. | Android dev |
| ☐ | Build account deletion | In the app and through a web link. Google Play requires both when users can create accounts [20]. | Developers |
| ☐ | Write the test plan | Cover login and guest mode, browse and search, inquiry, payment (test mode), consignment with photo upload, chatbot, tickets, admin and account deletion. | QA tester |
| ☐ | Prepare test devices | Low-end phone, mid-range phone, an older Android version, small and large screens, slow mobile data. | QA tester |
| ☐ | Use sample data only | Own photos or free-licence images. Never real customer data in testing. | QA tester |
| ☐ | Set up the internal testing track | Fast test builds for the team and A&J staff. Collect tester emails. | Project lead |
| ☐ | Check basic accessibility | Large text, colour contrast, screen-reader labels, tap-target size. | Designer + QA |

## Stage 3 – Before publishing

| Done | What to prepare | Details | Owner |
| --- | --- | --- | --- |
| ☐ | Confirm the app targets Android 16 (API 36) | Required for new apps and updates from 31 August 2026 [19]. | Android dev |
| ☐ | Publish the Privacy Notice on a public web page | Link it in Play Console and inside the app. | Project lead |
| ☐ | Complete the Data safety form | Must match what the app and its tools (Firebase, Supabase, PayMongo) actually collect. Includes the deletion questions [20]. | Project lead + backend dev |
| ☐ | Complete the content rating questionnaire and target audience | Set the audience as adults; the app is not made for children. | Project lead |
| ☐ | Give reviewers app access | A test login and short instructions so Google can review logged-in screens. | Project lead |
| ☐ | Answer the remaining App content declarations | Ads (none), government app (no) and others, answered truthfully. | Project lead |
| ☐ | Prepare the store listing | App name, short and full description, app icon, feature graphic and phone screenshots. Check current size limits in Play Console. No brand logos that suggest brand endorsement. No A&J website pictures. | Designer + project lead |
| ☐ | Run the closed test | A&J staff and selected customers. Fix crashes, freezes (ANRs) and issues in the Play pre-launch report. | QA tester |
| ☐ | Fix penetration-test findings | Fix all high and critical findings. Accept any remaining risk in writing. | Developers |
| ☐ | Turn on backups and test one restore | Prove the data can be recovered before real users arrive. | Backend dev |
| ☐ | Get legal sign-off | Terms, Privacy Notice, consignment terms and consent screens approved by the lawyer and A&J. | Project lead |
| ☐ | Plan a staged roll-out | For example 10%, then 50%, then 100% of users. Allow several days for Google's review of a new app. | Project lead |

## Stage 4 – After launch

| Done | What to prepare | Details | Owner |
| --- | --- | --- | --- |
| ☐ | Watch crashes and freezes | Check Android vitals and Crashlytics daily for 2 weeks, then weekly. Pause the roll-out if crashes spike. | Developers |
| ☐ | Reply to Play Store reviews | Aim for a reply within 2 business days. | Support staff |
| ☐ | Watch usage and bills | Supabase, Firebase and AI API usage. Set billing alerts. | Project lead |
| ☐ | Apply security updates monthly | Update libraries, review admin access, remove ex-staff accounts. | Maintenance dev |
| ☐ | Test a backup restore every quarter | Keeps the recovery plan proven. | Maintenance dev |
| ☐ | Keep a data breach plan | The Data Privacy Act rules expect notice to the NPC and affected people within 72 hours of learning of a breach (confirm with the lawyer). | DPO |
| ☐ | Track results | Downloads, active users, inquiries, consignments, chatbot hand-offs, ticket response time. | Project lead |
| ☐ | Keep chatbot answers and policies up to date | Review the top unanswered questions monthly. Keep the app and website saying the same thing. | A&J + project lead |
| ☐ | Do the yearly tasks | Update the Android target level before Google's yearly deadline, renew the domain and NPC registration, re-run a security test. | Maintenance dev + DPO |
| ☐ | Read Google Play policy emails | Act before the stated deadlines. Update the Data safety form and Privacy Notice whenever features change. | Project lead |

# 5. Three-month Gantt chart

Bars in the same week columns run in parallel. Dashed lines mark milestones M1 to M5.

## 5.1 Task table

Week numbers count from the project start (W1 to W12). The critical path is: 1.3 → 3.1 → 3.3 → 4.2 → 4.4 → M3 → 7.3/7.4 → M4 → 8.4 → M5. A delay on any of these moves the launch date.

| ID | Task | Start week | End week | Depends on | Owner | Runs in parallel with |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1: Planning and requirements |  |  |  |  |  |  |
| 1.1 | Kick-off, scope and feature sign-off | W1 | W1 | - | Project lead + A&J | 1.2, 1.3, 1.4 |
| 1.2 | Confirm policies with A&J (fees, returns, consignment) | W1 | W2 | - | Project lead + A&J | 1.3, 1.4 |
| 1.3 | Architecture and data model | W1 | W2 | - | Backend developer | 1.2, 1.4 |
| 1.4 | Open Play Console org account, D-U-N-S, emails | W1 | W2 | - | Project lead | 1.2, 1.3 |
| Phase 2: UI/UX design |  |  |  |  |  |  |
| 2.1 | Wireframes and user flows | W2 | W3 | 1.1 | UI/UX designer | 3.1 |
| 2.2 | High-fidelity app screens and style guide | W3 | W5 | 2.1 | UI/UX designer | 3.1, 3.2, 5.1 |
| 2.3 | Admin dashboard screens | W4 | W5 | 2.1 | UI/UX designer | 2.2, 4.1 |
| 2.4 | Quick usability check (5 users) | W5 | W5 | 2.2 | UI/UX designer | 4.1, 3.3 |
| Phase 3: Backend and database |  |  |  |  |  |  |
| 3.1 | Database, storage and security rules (staging + live) | W2 | W4 | 1.3 | Backend developer | 2.1, 2.2 |
| 3.2 | Login, guest access, photo storage | W3 | W4 | 3.1 | Backend developer | 2.2 |
| 3.3 | APIs: catalog, inquiries, consignment, tickets | W4 | W6 | 3.1 | Backend developer | 4.1, 4.2 |
| 3.4 | Payment provider in test mode (optional) | W6 | W7 | 3.3 | Backend developer | 4.2, 5.2 |
| Phase 4: Core features |  |  |  |  |  |  |
| 4.1 | App shell, navigation, login and guest mode | W4 | W5 | 2.2 (first screens), 3.2 | Android developer | 2.3, 3.3 |
| 4.2 | Browse, search, filters, item page, wishlist | W5 | W7 | 4.1, 3.3 | Android developer | 3.4, 6.1 |
| 4.3 | Buying: inquiry, payment, order tracker | W7 | W8 | 4.2 | Android developer | 4.4, 5.2 |
| 4.4 | Consignment: submit with photos, tracker | W7 | W9 | 4.2 | Android developer | 4.3, 5.3, 6.1 |
| Phase 5: Chatbot and support |  |  |  |  |  |  |
| 5.1 | Write and approve chatbot answers (FAQ) | W3 | W5 | 1.2 | Project lead + A&J | 2.2, 3.1 |
| 5.2 | Chatbot (FAQ; AI model optional) | W6 | W8 | 5.1, 3.3 | Backend developer | 4.2, 4.3 |
| 5.3 | Support tickets, agent hand-off, push alerts | W8 | W9 | 5.2 | Backend + Android dev | 4.4, 6.1 |
| Phase 6: Admin dashboard and reports |  |  |  |  |  |  |
| 6.1 | Admin web: listings, inquiries, consignments, tickets | W6 | W9 | 2.3, 3.3 | Backend developer | 4.2 to 4.4 |
| 6.2 | Reports, analytics events, CSV/PDF export | W9 | W10 | 6.1 | Backend developer | 7.2 |
| Phase 7: Testing and bug fixing |  |  |  |  |  |  |
| 7.1 | Test plan and test cases | W6 | W7 | 2.2 | QA tester | 4.2, 6.1 |
| 7.2 | Functional and device testing (internal track) | W8 | W10 | 7.1, 4.3 | QA tester | 4.4, 6.2 |
| 7.3 | Security check / penetration test | W10 | W11 | M3 | External security firm | 7.4, 8.3 |
| 7.4 | Closed test with A&J staff and customers | W10 | W11 | M3 | QA tester + A&J | 7.3, 8.2 |
| 7.5 | Bug fixing and performance | W9 | W12 | 7.2 | Android + backend dev | 7.2 to 7.4 |
| Phase 8: Publishing prep and release |  |  |  |  |  |  |
| 8.1 | Privacy notice, Terms, consignment terms (legal review) | W4 | W8 | 1.2 | Project lead + lawyer | most build tasks |
| 8.2 | Store listing: text, screenshots, graphics | W9 | W10 | 2.2 | UI/UX designer | 6.2, 7.2 |
| 8.3 | Data safety form, content rating, app signing | W10 | W11 | 8.1 | Project lead + Android dev | 7.3, 7.4 |
| 8.4 | Submit to Google Play for review | W11 | W12 | M4 | Project lead | 7.5 |
| 8.5 | Staged roll-out and launch monitoring | W12 | W12 | 8.4 | Whole team | 7.5 |

## 5.2 Milestones

| ID | Milestone | End of week | What “done” means |
| --- | --- | --- | --- |
| M1 | Requirements signed off | W2 | Feature list, policies and architecture signed off by A&J. |
| M2 | Design approved | W5 | App and admin screens approved; development follows the approved design. |
| M3 | Core features complete | W9 | Login, browsing, buying, consignment, chatbot, tickets and admin work end to end. No new features after this. |
| M4 | Release candidate ready | W11 | Closed test and security test passed; listing and declarations complete. |
| M5 | Public launch | W12 | App approved by Google and rolled out to the public. |

## 5.3 Work that runs in parallel

- Weeks 1–2: planning, architecture and the Play Console account set-up all run at once.

- Weeks 2–5: design runs alongside database set-up and writing the chatbot answers.

- Weeks 4–9: the Android developer builds app screens while the backend developer builds APIs, chatbot and admin website.

- Weeks 4–8: legal review runs in the background during the build.

- Weeks 9–12: testing, bug fixing, store listing and Play Console declarations overlap.

- Risk: Google's review of a new app can take several days or longer. If the review runs past week 12, launch moves into week 13.

# 6. Uncertain or unavailable information

- Exchange rate: no verified October 2026 USD to PHP rate was found. ₱61 is based on early August 2026 [6].

- Lawyer fees: no published Philippine rates for a privacy notice or terms review were found. ₱60,000 is an estimate; ask two firms for written quotes [18].

- NPC fees: the NPC fee schedule exists (Circular 2023-01), but the amount for registration could not be found. Whether A&J must register depends on its size and data volume [16].

- Penetration test: no Philippine price list was found. Global guides range from US$1,500 to US$35,000 [15]. Get local quotes.

- Salaries for the backend developer, designer, QA tester and project lead are estimates; only the Android developer rate is backed by salary data [17].

- AI chatbot: Claude Haiku 4.5 rates (US$1 input / US$5 output per million tokens) come from a site quoting Anthropic's price page [9]. Reports of a cheaper Haiku 5.5 rate could not be confirmed on the official page.

- Google Workspace: the ₱280 price is from a reseller. Google's own Philippine price was not found [8].

- Several prices come from third-party pricing guides, not the vendor's own page (Figma, GitHub, Sentry, Freshdesk, Supabase details). Check vendor pages before buying.

- Items marked E without a source (PayMongo set-up, Supabase backups and recovery add-on, Firebase Test Lab quota, D-U-N-S being free) are from general knowledge and were not re-checked.

- Legal points (Data Privacy Act, Internet Transactions Act, 72-hour breach notice) are general information, not legal advice. Confirm with counsel.

# 7. Sources

All web pages were checked on 23–24 October 2026. Prices change; confirm before paying.

[1] Google Play Console Help – developer registration fee
https://support.google.com/googleplay/android-developer/answer/6112435

[2] Google Play Payments policy (physical goods exclusion)
https://support.google.com/googleplay/android-developer/answer/9858738

[3] PayMongo – Fees and rates
https://developers.paymongo.com/docs/fees-and-rates

[4] Supabase – Pricing
https://supabase.com/pricing

[5] Firebase – Pricing
https://firebase.google.com/pricing

[6] ValutaFX – USD to PHP, 4 August 2026
https://www.valutafx.com/history/usd-php-2026-08-04

[7] DomainOffer – .com.ph price comparison (22 July 2026)
https://domainoffer.net/price-compare-com.ph

[8] Z.com Philippines – Google Workspace plans
https://web.z.com/ph/google-workspace/

[9] Claude Haiku 4.5 pricing (aggregator); official page
https://anotherwrapper.com/llm-pricing/claude-haiku-4-5-20251001

https://platform.claude.com/docs/en/about-claude/pricing

[10] Banani – Figma pricing 2026
https://www.banani.co/blog/figma-pricing-and-credits

[11] Spendflo – GitHub pricing guide
https://www.spendflo.com/blog/github-pricing-guide

[12] Capterra – Sentry pricing
https://www.capterra.com/p/165426/Sentry/pricing/

[13] Pinoy Techno Guide – Samsung Galaxy A16 LTE and 5G prices
https://www.pinoytechnoguide.com/smartphones/samsung-galaxy-a16-lte

https://www.pinoytechnoguide.com/smartphones/samsung-galaxy-a16-5g

[14] Drag – Freshdesk pricing 2026
https://www.dragapp.com/blog/freshdesk-pricing/

[15] Penetration testing cost guides
https://www.cycognito.com/learn/penetration-testing/penetration-testing-costs/

https://logsight.securelayer7.net/penetration-testing-cost/

[16] Baker McKenzie – NPC schedule of registration fees; NDV Law – NPC registration guide
https://insightplus.bakermckenzie.com/bm/data-technology/philippines-national-privacy-commission-implements-schedule-of-registration-fees-and-updated-procedure-on-submission-of-sworn-declaration-and-undertaking

https://ndvlaw.com/a-ceos-guide-to-registration-of-data-processing-system-with-the-national-privacy-commission-part-2-procedures-exceptions-and-practical-implications/

[17] Android developer salaries, Philippines (Indeed, NodeFlair)
https://ph.indeed.com/career/android-developer/salaries

https://nodeflair.com/salaries/philippines-android-developer-salary

[18] Respicio & Co. – Corporate lawyer retainers in the Philippines
https://www.respicio.ph/commentaries/corporate-lawyer-monthly-retainer-in-the-philippines-typical-scope-and-fees

[19] Android Developers – Target API level requirements
https://developer.android.com/google/play/requirements/target-sdk

[20] Google Play Console Help – Account deletion requirements
https://support.google.com/googleplay/android-developer/answer/13327111

[21] Testers Community – Cost and testing rules for publishing on Google Play
https://www.testerscommunity.com/blog/how-much-does-it-cost-to-publish-an-app-on-google-play

[22] KPMG – Philippines VAT on digital services (June 2026)
https://kpmg.com/us/en/taxnewsflash/news/2026/06/philippines-vat-digital-services.html